## Query
WITH
subqueryTable0 AS (
SELECT DISTINCT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable1 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Description AS CostCodeDesc_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable2 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Phase_Code AS CostCode_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable3 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Company_Code AS CompanyUniqueID_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable4 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Cost_Type AS CostType_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable5 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Job_Number AS ProjectUniqueID_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable6 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
SUM(table0.Original_Est_Hours) AS OriginalHours_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable7 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Status_Code AS projectstatus__custom_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable8 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
SUM(table0.Original_Est_Cost) AS OrigDollarEst_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable9 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
table0.Description AS Description,
table0.Phase_Job_Number AS Phase_Job_Number,
table0.Cost_Center AS Cost_Center,
table0.Status_Code AS Status_Code,
table0.Cost_Center AS phasecenter__standard_MAPPING
FROM
PHASE_MASTER
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type, table0.Description, table0.Phase_Job_Number,
table0.Cost_Center, table0.Status_Code
),
subqueryTable10 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type
FROM
COMMITTED_SUMMARY
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable11 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
(SUM(table0.PO_Ordered_Cost) - SUM(table0.PO_Received_Cost))
AS OpenCommitmentsMaterials_MAPPING
FROM
COMMITTED_SUMMARY
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable12 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type
FROM
TRANSACTIONS
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable13 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
SUM(table0.Total_Hours) AS Total_Hours__standard_MAPPING
FROM
TRANSACTIONS
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable14 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
SUM(table0.Total_Hours) AS JTDHours_MAPPING
FROM
TRANSACTIONS
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable15 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
SUM(table0.Tran_Amount) AS JTDCost_MAPPING
FROM
TRANSACTIONS
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable16 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
SUM(table0.Tran_Amount) AS BurdenCost_MAPPING
FROM
TRANSACTIONS
AS table0
WHERE ((table0.Cost_Type IN ('B')))
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable17 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type
FROM
PHASE_ESTIMATE
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable18 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
SUM(table0.Est_Hours) AS CurrentHours_MAPPING
FROM
PHASE_ESTIMATE
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable19 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
table0.Phase_Code AS Phase_Code,
table0.Cost_Type AS Cost_Type,
SUM(table0.Est_Cost) AS CurrentDollarEst_MAPPING
FROM
PHASE_ESTIMATE
AS table0
GROUP BY
table0.Company_Code, table0.Job_Number, table0.Phase_Code,
table0.Cost_Type
),
subqueryTable20 AS (
SELECT table0.Company_Code AS Company_Code, table0.Job_Number AS Job_Number
FROM
REVENUE
AS table0
GROUP BY table0.Company_Code, table0.Job_Number
),
subqueryTable21 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
SUM(table0.Earned_Revenue) AS JTD_Revenue_MAPPING
FROM
REVENUE
AS table0
GROUP BY table0.Company_Code, table0.Job_Number
),
subqueryTable22 AS (
SELECT table0.Company_Code AS Company_Code, table0.Job_Number AS Job_Number
FROM
CR_PAY
AS table0
GROUP BY table0.Company_Code, table0.Job_Number
),
subqueryTable23 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
SUM(table0.Payment_Amount) AS JTDCollected_MAPPING
FROM
CR_PAY
AS table0
GROUP BY table0.Company_Code, table0.Job_Number
),
subqueryTable24 AS (
SELECT table0.Company_Code AS Company_Code, table0.Job_Number AS Job_Number
FROM
ALT_BILLING
AS table0
GROUP BY table0.Company_Code, table0.Job_Number
),
subqueryTable25 AS (
SELECT
table0.Company_Code AS Company_Code,
table0.Job_Number AS Job_Number,
SUM(table0.Invoice_Amount) AS JTDGrossBillings_MAPPING
FROM
ALT_BILLING
AS table0
GROUP BY table0.Company_Code, table0.Job_Number
)
SELECT
subqueryTable1.CostCodeDesc_MAPPING AS CostCodeDesc,
subqueryTable2.CostCode_MAPPING AS CostCode,
subqueryTable3.CompanyUniqueID_MAPPING AS CompanyUniqueID,
subqueryTable4.CostType_MAPPING AS CostType,
subqueryTable5.ProjectUniqueID_MAPPING AS ProjectUniqueID,
subqueryTable6.OriginalHours_MAPPING AS OriginalHours,
subqueryTable7.projectstatus__custom_MAPPING AS projectstatus__custom,
subqueryTable8.OrigDollarEst_MAPPING AS OrigDollarEst,
subqueryTable9.phasecenter__standard_MAPPING AS phasecenter__standard,
subqueryTable11.OpenCommitmentsMaterials_MAPPING AS OpenCommitmentsMaterials,
subqueryTable13.Total_Hours__standard_MAPPING AS Total_Hours__standard,
subqueryTable14.JTDHours_MAPPING AS JTDHours,
subqueryTable15.JTDCost_MAPPING AS JTDCost,
subqueryTable16.BurdenCost_MAPPING AS BurdenCost,
subqueryTable18.CurrentHours_MAPPING AS CurrentHours,
subqueryTable19.CurrentDollarEst_MAPPING AS CurrentDollarEst,
subqueryTable21.JTD_Revenue_MAPPING AS JTD_Revenue,
subqueryTable23.JTDCollected_MAPPING AS JTDCollected,
subqueryTable25.JTDGrossBillings_MAPPING AS JTDGrossBillings,
CASE
WHEN (subqueryTable5.ProjectUniqueID_MAPPING IS NOT NULL)
THEN
CONCAT(
IFNULL(subqueryTable2.CostCode_MAPPING, ""),
" - ",
IFNULL(subqueryTable1.CostCodeDesc_MAPPING, ""))
ELSE
CONCAT(
IFNULL(subqueryTable2.CostCode_MAPPING, ""),
" - ",
IFNULL(subqueryTable1.CostCodeDesc_MAPPING, ""))
END AS Phase_Code,
"2026-01-31" AS EOPeriodDate,
"1" AS Period,
"2026" AS Year,
CAST('2026-01-05 20:32:16' AS DATETIME) AS BQInsertTimeUTC,
'praveen.kumar@discretus-latere.com' AS ModifiedBy
FROM subqueryTable0 AS maintable
LEFT JOIN subqueryTable1
ON (
maintable.Company_Code = subqueryTable1.Company_Code
AND maintable.Job_Number = subqueryTable1.Job_Number
AND maintable.Phase_Code = subqueryTable1.Phase_Code
AND maintable.Cost_Type = subqueryTable1.Cost_Type
AND maintable.Description = subqueryTable1.Description
AND maintable.Phase_Job_Number = subqueryTable1.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable1.Cost_Center
AND maintable.Status_Code = subqueryTable1.Status_Code)
LEFT JOIN subqueryTable2
ON (
maintable.Company_Code = subqueryTable2.Company_Code
AND maintable.Job_Number = subqueryTable2.Job_Number
AND maintable.Phase_Code = subqueryTable2.Phase_Code
AND maintable.Cost_Type = subqueryTable2.Cost_Type
AND maintable.Description = subqueryTable2.Description
AND maintable.Phase_Job_Number = subqueryTable2.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable2.Cost_Center
AND maintable.Status_Code = subqueryTable2.Status_Code)
LEFT JOIN subqueryTable3
ON (
maintable.Company_Code = subqueryTable3.Company_Code
AND maintable.Job_Number = subqueryTable3.Job_Number
AND maintable.Phase_Code = subqueryTable3.Phase_Code
AND maintable.Cost_Type = subqueryTable3.Cost_Type
AND maintable.Description = subqueryTable3.Description
AND maintable.Phase_Job_Number = subqueryTable3.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable3.Cost_Center
AND maintable.Status_Code = subqueryTable3.Status_Code)
LEFT JOIN subqueryTable4
ON (
maintable.Company_Code = subqueryTable4.Company_Code
AND maintable.Job_Number = subqueryTable4.Job_Number
AND maintable.Phase_Code = subqueryTable4.Phase_Code
AND maintable.Cost_Type = subqueryTable4.Cost_Type
AND maintable.Description = subqueryTable4.Description
AND maintable.Phase_Job_Number = subqueryTable4.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable4.Cost_Center
AND maintable.Status_Code = subqueryTable4.Status_Code)
LEFT JOIN subqueryTable5
ON (
maintable.Company_Code = subqueryTable5.Company_Code
AND maintable.Job_Number = subqueryTable5.Job_Number
AND maintable.Phase_Code = subqueryTable5.Phase_Code
AND maintable.Cost_Type = subqueryTable5.Cost_Type
AND maintable.Description = subqueryTable5.Description
AND maintable.Phase_Job_Number = subqueryTable5.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable5.Cost_Center
AND maintable.Status_Code = subqueryTable5.Status_Code)
LEFT JOIN subqueryTable6
ON (
maintable.Company_Code = subqueryTable6.Company_Code
AND maintable.Job_Number = subqueryTable6.Job_Number
AND maintable.Phase_Code = subqueryTable6.Phase_Code
AND maintable.Cost_Type = subqueryTable6.Cost_Type
AND maintable.Description = subqueryTable6.Description
AND maintable.Phase_Job_Number = subqueryTable6.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable6.Cost_Center
AND maintable.Status_Code = subqueryTable6.Status_Code)
LEFT JOIN subqueryTable7
ON (
maintable.Company_Code = subqueryTable7.Company_Code
AND maintable.Job_Number = subqueryTable7.Job_Number
AND maintable.Phase_Code = subqueryTable7.Phase_Code
AND maintable.Cost_Type = subqueryTable7.Cost_Type
AND maintable.Description = subqueryTable7.Description
AND maintable.Phase_Job_Number = subqueryTable7.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable7.Cost_Center
AND maintable.Status_Code = subqueryTable7.Status_Code)
LEFT JOIN subqueryTable8
ON (
maintable.Company_Code = subqueryTable8.Company_Code
AND maintable.Job_Number = subqueryTable8.Job_Number
AND maintable.Phase_Code = subqueryTable8.Phase_Code
AND maintable.Cost_Type = subqueryTable8.Cost_Type
AND maintable.Description = subqueryTable8.Description
AND maintable.Phase_Job_Number = subqueryTable8.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable8.Cost_Center
AND maintable.Status_Code = subqueryTable8.Status_Code)
LEFT JOIN subqueryTable9
ON (
maintable.Company_Code = subqueryTable9.Company_Code
AND maintable.Job_Number = subqueryTable9.Job_Number
AND maintable.Phase_Code = subqueryTable9.Phase_Code
AND maintable.Cost_Type = subqueryTable9.Cost_Type
AND maintable.Description = subqueryTable9.Description
AND maintable.Phase_Job_Number = subqueryTable9.Phase_Job_Number
AND maintable.Cost_Center = subqueryTable9.Cost_Center
AND maintable.Status_Code = subqueryTable9.Status_Code)
LEFT JOIN subqueryTable10
ON (
maintable.Company_Code = subqueryTable10.Company_Code
AND maintable.Phase_Job_Number = subqueryTable10.Job_Number
AND maintable.Phase_Code = subqueryTable10.Phase_Code
AND maintable.Cost_Type = subqueryTable10.Cost_Type)
LEFT JOIN subqueryTable11
ON (
maintable.Company_Code = subqueryTable11.Company_Code
AND maintable.Phase_Job_Number = subqueryTable11.Job_Number
AND maintable.Phase_Code = subqueryTable11.Phase_Code
AND maintable.Cost_Type = subqueryTable11.Cost_Type)
LEFT JOIN subqueryTable12
ON (
maintable.Company_Code = subqueryTable12.Company_Code
AND maintable.Phase_Job_Number = subqueryTable12.Job_Number
AND maintable.Phase_Code = subqueryTable12.Phase_Code
AND maintable.Cost_Type = subqueryTable12.Cost_Type)
LEFT JOIN subqueryTable13
ON (
maintable.Company_Code = subqueryTable13.Company_Code
AND maintable.Phase_Job_Number = subqueryTable13.Job_Number
AND maintable.Phase_Code = subqueryTable13.Phase_Code
AND maintable.Cost_Type = subqueryTable13.Cost_Type)
LEFT JOIN subqueryTable14
ON (
maintable.Company_Code = subqueryTable14.Company_Code
AND maintable.Phase_Job_Number = subqueryTable14.Job_Number
AND maintable.Phase_Code = subqueryTable14.Phase_Code
AND maintable.Cost_Type = subqueryTable14.Cost_Type)
LEFT JOIN subqueryTable15
ON (
maintable.Company_Code = subqueryTable15.Company_Code
AND maintable.Phase_Job_Number = subqueryTable15.Job_Number
AND maintable.Phase_Code = subqueryTable15.Phase_Code
AND maintable.Cost_Type = subqueryTable15.Cost_Type)
LEFT JOIN subqueryTable16
ON (
maintable.Company_Code = subqueryTable16.Company_Code
AND maintable.Phase_Job_Number = subqueryTable16.Job_Number
AND maintable.Phase_Code = subqueryTable16.Phase_Code
AND maintable.Cost_Type = subqueryTable16.Cost_Type)
LEFT JOIN subqueryTable17
ON (
maintable.Company_Code = subqueryTable17.Company_Code
AND maintable.Phase_Job_Number = subqueryTable17.Job_Number
AND maintable.Phase_Code = subqueryTable17.Phase_Code
AND maintable.Cost_Type = subqueryTable17.Cost_Type)
LEFT JOIN subqueryTable18
ON (
maintable.Company_Code = subqueryTable18.Company_Code
AND maintable.Phase_Job_Number = subqueryTable18.Job_Number
AND maintable.Phase_Code = subqueryTable18.Phase_Code
AND maintable.Cost_Type = subqueryTable18.Cost_Type)
LEFT JOIN subqueryTable19
ON (
maintable.Company_Code = subqueryTable19.Company_Code
AND maintable.Phase_Job_Number = subqueryTable19.Job_Number
AND maintable.Phase_Code = subqueryTable19.Phase_Code
AND maintable.Cost_Type = subqueryTable19.Cost_Type)
LEFT JOIN subqueryTable20
ON (
maintable.Company_Code = subqueryTable20.Company_Code
AND maintable.Phase_Job_Number = subqueryTable20.Job_Number)
LEFT JOIN subqueryTable21
ON (
maintable.Company_Code = subqueryTable21.Company_Code
AND maintable.Phase_Job_Number = subqueryTable21.Job_Number)
LEFT JOIN subqueryTable22
ON (
maintable.Company_Code = subqueryTable22.Company_Code
AND maintable.Phase_Job_Number = subqueryTable22.Job_Number)
LEFT JOIN subqueryTable23
ON (
maintable.Company_Code = subqueryTable23.Company_Code
AND maintable.Phase_Job_Number = subqueryTable23.Job_Number)
LEFT JOIN subqueryTable24
ON (
maintable.Company_Code = subqueryTable24.Company_Code
AND maintable.Phase_Job_Number = subqueryTable24.Job_Number)
LEFT JOIN subqueryTable25
ON (
maintable.Company_Code = subqueryTable25.Company_Code
AND maintable.Phase_Job_Number = subqueryTable25.Job_Number)

## Summary
|  |  | Job Name |  | JOINT RESERVE BASE HANGAR
|  |  | Job No. |  | 643700
|  |  | Project Manager |  | J RAMOS
|  |  | Report Date |  | 2026-01-07
As of Date
| Revised Contract | Notice to Proceed | Pending | Pending Contract | Projected | Variance | Prior Month Variance
Revenue | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Labor | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0
Burden | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #DIV/0! | #DIV/0!
Material / Subcontracts | #REF! | #REF! | #REF! | #REF! | 473279.63 | #REF! | -473279.63
DJE / Other | #REF! | #REF! | #REF! | #REF! | 29087.91 | #REF! | -29087.91
Total Cost | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #DIV/0!
Profit | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Profit % on Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Profit % on Rev | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FINANCIAL AND OPERATIONAL DASHBOARD FOR THIS REPORTING PERIOD
Over/ (Under) Billings |  |  |  | Project Cash to Cost Position
JTD Gross Billings $ | None |  |  | JTD Collected $ | None
JTD Revenue $ | None |  |  | JTD Cost $ | 24375.4
Over/ (Under) Billing $ | #VALUE! |  |  | Net Cash Position $ | #VALUE!
As of Date: | 2025-12-31 |  |  | As of Date: | 2025-12-31
Composite Rate Analysis |  |  |  | Labor Performance Factor |  |  | Prior Month
Composite Rate (Est.) | #REF! |  |  | Earned MH's | #REF! | #REF! | #REF! | #REF!
Composite Rate (Act.) | 51.69 |  |  | Actual MH's | 290 | 14990.1 | 290 | 14990.1
Composite Rate Var | #REF! |  |  | Labor Performance Factor | #REF! | #REF! | #REF! | #REF!
As of Date: | 2025-12-31 |  |  | As of Date: | 2025-12-31
A/R Aged Open Items |  |  |  | Estimated % Complete @ YE value | 3%
Current | None
1-30 Days | None |  |  | Bid day Labor Performance Factor
31-60 Days | None
61-90 Days | None
Over 90 Days | None
Last Billing Date | NaT
NOTES REGARDING SCHEDULE, JOB PROGRESS, CONCERNS:

## Manpower Projection
JOINT RESERVE BASE HANGAR
[7 empty] | Burden Cost | Labor Cost | Total Hours
|  |  |  | 9240.130000000 |  |  | #REF! | #REF! | #REF!
Projection Labor & Burden
Job Projection
Projection Labor Rate |  |  | #DIV/0!
Projection L&B Rate |  |  | #DIV/0!
Week Ending: |  | Total Hrs | Labor Cost | Burden Cost | Total Cost | Labor / Hr | L&B / Hr
Job to Date |  | 290 | 14989.17 | 9240.130000000 | 24229.3 | 51.69 | 83.5493
Projection to Complete |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total Projection |  | 290 | 14989.17 | 9240.13 | #DIV/0! | 51.6868 | #DIV/0!
Bid + Change Orders |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 290
Variance |  | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #DIV/0!
|  | Average Crew | Ave Hrs | Ave Days | Total Hrs | Labor Projection | Delta | Avg Composite Rate | Avg L&B Rate
Manpower Projection |  | 4.5455 | 10 | 4 | 0 | 12624.4758 | -12624.4758 | 51.69 | 83.5493
Grand Total | - | 50 | 110 | 44 | 2000 | - | - | 2584.5 | 4177.4655
Week ending: | Actual Manpower | Estimated Manpower | Hours/Day | Days/Week | Total Hours | Composite Rate | L&B Rate | Avg Composite Rate | Avg L&B Rate
2025-11-07 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2025-11-14 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2025-11-21 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2025-11-28 | 2 | 2 | 10 | 4 | 80 | 51.69 | 83.5493 | 103.38 | 167.0986
2025-12-05 | 2 | 2 | 10 | 4 | 80 | 51.69 | 83.5493 | 103.38 | 167.0986
2025-12-12 | 2 | 2 | 10 | 4 | 80 | 51.69 | 83.5493 | 103.38 | 167.0986
2025-12-19 | 2 | 2 | 10 | 4 | 80 | 51.69 | 83.5493 | 103.38 | 167.0986
2025-12-26 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-01-02 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-01-09 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-01-16 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-01-23 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-01-30 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-02-06 | 6 | 6 | 10 | 4 | 240 | 51.69 | 83.5493 | 310.14 | 501.2959
2026-02-13 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-02-20 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-02-27 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-03-06 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-03-13 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-03-20 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-03-27 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-04-03 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-04-10 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-04-17 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-04-24 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-05-01 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-05-08 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-05-15 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-05-22 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-05-29 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-06-05 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-06-12 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-06-19 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-06-26 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-07-03 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-07-10 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-07-17 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-07-24 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-07-31 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-08-07 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-08-14 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-08-21 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-08-28 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-09-04 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-09-11 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-09-18 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-09-25 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-10-02 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-10-09 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-10-16 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-10-23 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-10-30 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-11-06 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-11-13 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-11-20 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-11-27 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-12-04 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-12-11 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-12-18 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2026-12-25 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
2027-01-01 |  |  |  |  | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0
[5 empty] | 0 | 51.69 | 83.5493 | 0 | 0

## Labor Projection
| JOINT RESERVE BASE HANGAR | [5 empty] | -12624.4758 | Projected Composite Rate: |  | #DIV/0! | Projected Burden Rate: |  | #DIV/0!
Job to Date Labor
Final | 12 | 2025 | 2025-12-31
|  |  | 12878 | 0 | #REF! | 290 | 2.246% | 12624.4758 |  | 0 | 12624.4758 | 12914.4758 | 36.4758 | 508684 | 0 | #REF! | 14989.17 | 0 | 0 | 0 | 790.0085 | 211.5114 | -578.4972
| Phase | Cost Type | Original Hours Estimate | Change Order Hours Estimate | Current Labor Hours Estimate | JTD Hours | Est. % Complete | Base Hrs to Complete | Productivity Factor | Productivity Hours | Projected Hrs to Complete | Total Hrs | (Under) / Over | Original Labor Dollar Est. | Change Order Labor Dollar Est. | Current Labor Dollar Estimate | JTD Labor Cost | Est Labor to Complete | Est. Total Labor | (Under) / Over | Est. $/Hour | JTD $/ Hr | (Under) / Over | CostType | PhaseCenter
| 00300321 - PROJECT ENGINEER | L | 0 | 0 | 0 | 16 |  | 0 |  | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 901.6 |  |  |  | 0 | 56.35 | 56.35 | L | 0050301000
| 00300321 - PROJECT ENGINEER | LA | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LA | 0050301000
| 00300321 - PROJECT ENGINEER | LB | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LB | 0050301000
| 00300321 - PROJECT ENGINEER | LD | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LD | 0050301000
| 00300321 - PROJECT ENGINEER | LM | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LM | 0050301000
| 00400000 - ALL LABOR | L | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | L | 0050301000
| 00400000 - ALL LABOR | LA | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LA | 0050301000
| 00400000 - ALL LABOR | LB | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LB | 0050301000
| 00400000 - ALL LABOR | LD | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LD | 0050301000
| 00400000 - ALL LABOR | LM | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LM | 0050301000
| 00400401 - LIGHT FIXTURES | L | 752 | 0 | 752 |  |  | 752 |  | 0 | 752 | 752 | 0 | 29704 | 0 | 29704 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400403 - BW- LIGHTING- ABOVE CEILI | L | 2600 | 0 | 2600 |  |  | 2600 |  | 0 | 2600 | 2600 | 0 | 102700 | 0 | 102700 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400404 - WIRING DEVICES- LIGHTING | L | 229 | 0 | 229 |  |  | 229 |  | 0 | 229 | 229 | 0 | 9046 | 0 | 9046 |  |  |  |  | 39.5022 | 0 | -39.5022 | L | 0050301000
| 00400405 - DISTRIBUTION RACEWAY & FE | L | 1600 | 0 | 1600 |  |  | 1600 |  | 0 | 1600 | 1600 | 0 | 63200 | 0 | 63200 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400408 - GEAR | L | 331 | 0 | 331 |  |  | 331 |  | 0 | 331 | 331 | 0 | 13075 | 0 | 13075 |  |  |  |  | 39.5015 | 0 | -39.5015 | L | 0050301000
| 00400409 - TEMPORARY | L | 360 | 0 | 360 | 131 | 36% | 232.8889 |  | 0 | 232.8889 | 363.8889 | 3.8889 | 14220 | 0 | 14220 | 6609.13 |  |  |  | 39.5 | 50.4514 | 10.9514 | L | 0050301000
| 00400413 - FIRE ALARM | L | 496 | 0 | 496 |  |  | 496 |  | 0 | 496 | 496 | 0 | 19592 | 0 | 19592 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400416 - DEMO | L | 180 | 0 | 180 | 80 | 44.3% | 100.5869 |  | 0 | 100.5869 | 180.5869 | 0.58691 | 7110 | 0 | 7110 | 4149.23 |  |  |  | 39.5 | 51.8654 | 12.3654 | L | 0050301000
| 00400417 - GROUNDING | L | 269 | 0 | 269 |  |  | 269 |  | 0 | 269 | 269 | 0 | 10626 | 0 | 10626 |  |  |  |  | 39.5019 | 0 | -39.5019 | L | 0050301000
| 00400418 - TECHNOLOGIES | L | 358 | 0 | 358 |  |  | 358 |  | 0 | 358 | 358 | 0 | 14141 | 0 | 14141 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400419 - SUPERVISION | L | 1484 | 0 | 1484 | 63 | 4.2% | 1437 |  | 0 | 1437 | 1500 | 16 | 58618 | 0 | 58618 | 3329.21 |  |  |  | 39.5 | 52.8446 | 13.3446 | L | 0050301000
| 00400420 - GENERATOR | L | 180 | 0 | 180 |  |  | 180 |  | 0 | 180 | 180 | 0 | 7110 | 0 | 7110 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400421 - UG DISTIBUTION/DB | L | 400 | 0 | 400 |  |  | 400 |  | 0 | 400 | 400 | 0 | 15800 | 0 | 15800 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400422 - MV CABLE | L | 360 | 0 | 360 |  |  | 360 |  | 0 | 360 | 360 | 0 | 14220 | 0 | 14220 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400423 - MV TERMINATIONS | L | 88 | 0 | 88 |  |  | 88 |  | 0 | 88 | 88 | 0 | 3476 | 0 | 3476 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400424 - START UP & COMMISIONING | L | 80 | 0 | 80 |  |  | 80 |  | 0 | 80 | 80 | 0 | 3160 | 0 | 3160 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00400425 - PUNCHLIST | L | 120 | 0 | 120 |  |  | 120 |  | 0 | 120 | 120 | 0 | 4740 | 0 | 4740 |  |  |  |  | 39.5 | 0 | -39.5 | L | 0050301000
| 00401402 - BW- POWER- HOMERUNS | L | 641 | 0 | 641 |  |  | 641 |  | 0 | 641 | 641 | 0 | 25320 | 0 | 25320 |  |  |  |  | 39.5008 | 0 | -39.5008 | L | 0050301000
| 00401403 - BW- POWER- ABOVE CEILING | L | 2093 | 0 | 2093 |  |  | 2093 |  | 0 | 2093 | 2093 | 0 | 82674 | 0 | 82674 |  |  |  |  | 39.5002 | 0 | -39.5002 | L | 0050301000
| 00401404 - WIRING DEVICES- POWER | L | 257 | 0 | 257 |  |  | 257 |  | 0 | 257 | 257 | 0 | 10152 | 0 | 10152 |  |  |  |  | 39.5019 | 0 | -39.5019 | L | 0050301000
| 00405450 - ENGRAVING TAGS | L | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | L | 0050301000
| 00405450 - ENGRAVING TAGS | LA | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LA | 0050301000
| 00405450 - ENGRAVING TAGS | LB | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LB | 0050301000
| 00405450 - ENGRAVING TAGS | LD | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LD | 0050301000
| 00405450 - ENGRAVING TAGS | LM | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | LM | 0050301000
| ABC | Pseudo Cost Type | Original Hours Estimate | Change Order Hours Estimate | Current Labor Hours Estimate | JTD Hours | Est. % Complete | Base Hrs to Complete | Productivity Factor | Productivity Hours | Projected Hrs to Complete | Total Hrs | (Under) / Over | Original Labor Dollar Est. | Change Order Labor Dollar Est. | Current Labor Dollar Estimate | JTD Labor Cost | Est Labor to Complete | Est. Total Labor | (Under)/Over | Est. $/Hour | JTD $/ Hr | (Under) / Over2
| NOTICE TO PROCEED LABOR HOURS |  |  |  | #REF! | [10 empty] | #REF!

## Materials
JOINT RESERVE BASE HANGAR
Material, Subcontract, Other & Tax
|  | Materials / Subcontracts | 1043578 | 0 | 1043578 | 146.1 | 429478.63 | 429624.73 | 43654.9 | 473279.63 | 0.03087% | 570298.37 | 54.65%
|  | DJE / Others | 383140 | 0 | 383140 | 0 | 29087.91 | 29087.91 | 0 | 29087.91 | 0% | 354052.09 | 92.41%
Summary Sheet Comparison
|  | Materials / Subcontracts | [9 empty] | #REF! | #REF!
|  | DJE / Others | [9 empty] | #REF! | #REF!
Grand Total | - | - | 1426718 | 0 | 1426718 | 146.1 | 458566.54 | 458712.64 | 43654.9 | 502367.54 | - | 924350.46 | - | - | -
Cost Type | CostType1 | Phase | Original Estimate | Change Orders Estimate | Current Estimate | JTD | Open | JTD + Open | Estimated Future Costs | Projected Cost | % Complete | Variance | % Variance | PhaseCenter | ProjectStatus
E | E | 00300306 - EQUIPMENT RENTAL | 96900 | 0 | 96900 |  | 26643.75 | 26643.75 |  | 26643.75 | 0% | 70256.25 | 72.5% | 0050301000 | A
E | E | 00300312 - STORAGE & SHEDS | 5000 | 0 | 5000 |  |  | 0 |  | 0 | 0% | 5000 | 100% | 0050301000 | A
E | E | 00300327 - OFFSITE STORAGE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
Subtotal of E | - | - | 101900 | 0 | 101900 | 0 | 26643.75 | 26643.75 | 0 | 26643.75 | - | 75256.25 | - | - | -
M | M | 00100000 - MISC MATERIALS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100010 - GALVANIZED CONDUIT & FITT | 4228 | 0 | 4228 |  |  | 0 |  | 0 | 0% | 4228 | 100% | 0050301000 | A
M | M | 00100020 - EMT CONDUIT & FITTINGS | 52019 | 0 | 52019 |  |  | 0 |  | 0 | 0% | 52019 | 100% | 0050301000 | A
M | M | 00100030 - PVC CONDUIT & FITTTINGS | 2982 | 0 | 2982 |  |  | 0 |  | 0 | 0% | 2982 | 100% | 0050301000 | A
M | M | 00100040 - FIBERGLASS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100050 - PVC COATED CONDUIT & FITT | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100060 - IMC CONDUIT & FITTINGS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100070 - ALUMINUM CONDUIT,FITTING | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100100 - MATERIALS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100130 - SUPPORTS | 43801 | 0 | 43801 | 146.1 | 0 | 146.1 | 43654.9 | 43801 | 0.3336% | 0 | 0% | 0050301000 | A
M | M | 00100140 - FLEXIBLE CONDUIT & FITTIN | 666 | 0 | 666 |  |  | 0 |  | 0 | 0% | 666 | 100% | 0050301000 | A
M | M | 00100170 - GROUNDING | 14476 | 0 | 14476 |  |  | 0 |  | 0 | 0% | 14476 | 100% | 0050301000 | A
M | M | 00100180 - FIXTURES & LAMPS & PARTS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100210 - WIRING DEVICES & WALL PLA | 1429 | 0 | 1429 |  |  | 0 |  | 0 | 0% | 1429 | 100% | 0050301000 | A
M | M | 00100230 - BOXES & FITTINGS | 10483 | 0 | 10483 |  | 226.3 | 226.3 |  | 226.3 | 0% | 10256.7 | 97.84% | 0050301000 | A
M | M | 00100290 - LOW VOLTAGE WIRING CABLE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100310 - COPPER WIRE | 155925 | 0 | 155925 |  |  | 0 |  | 0 | 0% | 155925 | 100% | 0050301000 | A
M | M | 00100350 - ALUMINUM WIRE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100370 - MC CABLE & FITTINGS | 6961 | 0 | 6961 |  |  | 0 |  | 0 | 0% | 6961 | 100% | 0050301000 | A
M | M | 00100390 - PORTABLE CORD & FITTINGS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100420 - WIRE TERMINATIONS | 1305 | 0 | 1305 |  | 3719.89 | 3719.89 |  | 3719.89 | 0% | -2414.89 | -185% | 0050301000 | A
M | M | 00100430 - SWITCHGEAR | 4667 | 0 | 4667 |  | 1653.44 | 1653.44 |  | 1653.44 | 0% | 3013.56 | 64.57% | 0050301000 | A
M | M | 00100470 - CONCRETE & ACCESSORIES | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100490 - FIREPROOFING | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100510 - SURFACE & UNDERFLOOR RACE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100550 - GUTTER & GUTTER FITTINGS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100560 - CABLE TRAY | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100580 - SPECIAL & LV SYSTEMS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100600 - FIREALARM | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100610 - NURSE CALL | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100620 - LIGHTNING PROTECTION | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100630 - TEMPERATURE CONTROLS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100640 - LOW VOLTAGE SYSTEMS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100710 - DEMOLITION | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100740 - TRENCHING,CONCRETE,MISC | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100770 - FIBER CABLE & ACCESSORIES | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100810 - CORING & HOLES | 733 | 0 | 733 |  |  | 0 |  | 0 | 0% | 733 | 100% | 0050301000 | A
M | M | 00100850 - CORD SETS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100890 - SUBCONTRACTORS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100970 - TEMPORARY POWER COMPONENT | 21651 | 0 | 21651 |  |  | 0 |  | 0 | 0% | 21651 | 100% | 0050301000 | A
M | M | 00100980 - OVERHEAD UTILITY ITEMS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00100990 - UNDEFINED ITEMS | 101 | 0 | 101 |  |  | 0 |  | 0 | 0% | 101 | 100% | 0050301000 | A
M | M | 00200201 - FIXTURES | 111640 | 0 | 111640 |  |  | 0 |  | 0 | 0% | 111640 | 100% | 0050301000 | A
M | M | 00200202 - GEAR | 180000 | -120000 | 60000 |  |  | 0 |  | 0 | 0% | 60000 | 100% | 0050301000 | A
M | M | 00200205 - GENERATOR | 0 | 120000 | 120000 |  | 120000 | 120000 |  | 120000 | 0% | 0 | 0% | 0050301000 | A
M | M | 00200206 - ATS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00200207 - UPS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00200208 - PDU | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00200210 - MANHOLES | 2825 | 0 | 2825 |  |  | 0 |  | 0 | 0% | 2825 | 100% | 0050301000 | A
M | M | 00200220 - MEDIUM VOLTAGE | 5726 | 0 | 5726 |  |  | 0 |  | 0 | 0% | 5726 | 100% | 0050301000 | A
M | M | 00200221 - CABLE TRAY | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00200223 - VEHICLE CHARGER | 10000 | 0 | 10000 |  |  | 0 |  | 0 | 0% | 10000 | 100% | 0050301000 | A
M | M | 00300318 - FREIGHT CHARGES | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
M | M | 00400450 - PREFAB | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
Subtotal of M | - | - | 631618 | 0 | 631618 | 146.1 | 125599.63 | 125745.73 | 43654.9 | 169400.63 | - | 462217.37 | - | - | -
O | O | 00100000 - MISC MATERIALS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300301 - PERMITS | 1200 | 0 | 1200 |  |  | 0 |  | 0 | 0% | 1200 | 100% | 0050301000 | A
O | O | 00300302 - UTILITY CHARGES | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300303 - SPECIAL INSURANCE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300305 - EXPENDABLES TOOLS/REPAIRS | 39722 | 0 | 39722 |  | 2444.16 | 2444.16 |  | 2444.16 | 0% | 37277.84 | 93.85% | 0050301000 | A
O | O | 00300307 - TOOL EXPENSE | 10000 | 0 | 10000 |  |  | 0 |  | 0 | 0% | 10000 | 100% | 0050301000 | A
O | O | 00300314 - TELEPHONE & CELL PH & IT | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300315 - AS BUILT DRAWINGS | 500 | 0 | 500 |  |  | 0 |  | 0 | 0% | 500 | 100% | 0050301000 | A
O | O | 00300316 - VEHICLE EXPENSE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300317 - TRAVEL EXPENSE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300319 - FIELD OFFICE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300320 - PM | 54770 | 0 | 54770 |  |  | 0 |  | 0 | 0% | 54770 | 100% | 0050301000 | A
O | O | 00300322 - CADD | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300323 - BOND EXPENSE | 39948 | 0 | 39948 |  |  | 0 |  | 0 | 0% | 39948 | 100% | 0050301000 | A
O | O | 00300324 - ENTERTAINMENT | 1800 | 0 | 1800 |  |  | 0 |  | 0 | 0% | 1800 | 100% | 0050301000 | A
O | O | 00300325 - LEGAL | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
O | O | 00300328 - SAFETY DRUG TESTING | 3300 | 0 | 3300 |  |  | 0 |  | 0 | 0% | 3300 | 100% | 0050301000 | A
O | O | 00300329 - DIESEL FUEL | 5000 | 0 | 5000 |  |  | 0 |  | 0 | 0% | 5000 | 100% | 0050301000 | A
O | O | 00300330 - LABOR CONTINGENCY | 115000 | 0 | 115000 |  |  | 0 |  | 0 | 0% | 115000 | 100% | 0050301000 | A
O | O | 00300331 - PACK | 10000 | 0 | 10000 |  |  | 0 |  | 0 | 0% | 10000 | 100% | 0050301000 | A
O | O | 00400450 - PREFAB | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
Subtotal of O | - | - | 281240 | 0 | 281240 | 0 | 2444.16 | 2444.16 | 0 | 2444.16 | - | 278795.84 | - | - | -
S | S | 00200203 - FIRE ALARM SUB CONTRACT | 203000 | 0 | 203000 |  | 203879 | 203879 |  | 203879 | 0% | -879 | -0.433% | 0050301000 | A
S | S | 00200204 - LIGHTNING PROTECTION | 95900 | 0 | 95900 |  | 95900 | 95900 |  | 95900 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200209 - TESTING | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200211 - DITCHING | 39000 | 0 | 39000 |  |  | 0 |  | 0 | 0% | 39000 | 100% | 0050301000 | A
S | S | 00200212 - CRANE | 4086 | 0 | 4086 |  |  | 0 |  | 0 | 0% | 4086 | 100% | 0050301000 | A
S | S | 00200213 - RIGGING/MOVERS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200214 - TELE/DATA | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200215 - SECURITY/CCTV | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200216 - NURSE CALL | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200217 - A/V | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200218 - CONTROLS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00200222 - SOLAR | 52974 | 0 | 52974 |  |  | 0 |  | 0 | 0% | 52974 | 100% | 0050301000 | A
S | S | 00200224 - SCANNING & CORING | 5500 | 0 | 5500 |  |  | 0 |  | 0 | 0% | 5500 | 100% | 0050301000 | A
S | S | 00200225 - HYDROVAC | 6500 | 0 | 6500 |  |  | 0 |  | 0 | 0% | 6500 | 100% | 0050301000 | A
S | S | 00200226 - CABLE TESTING | 5000 | 0 | 5000 |  | 4100 | 4100 |  | 4100 | 0% | 900 | 18% | 0050301000 | A
S | S | 00300308 - TRENCHING SUBCONTRACTOR | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00300309 - TESTING SERVICES | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00300310 - CRANE | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00300311 - CABLE TEST | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00300326 - CONTRACT LABOR | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
S | S | 00300399 - MISC SUBCONTRACTOR SVCS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
Subtotal of S | - | - | 411960 | 0 | 411960 | 0 | 303879 | 303879 | 0 | 303879 | - | 108081 | - | - | -
T | T | 00300304 - SALES TAX/ TARIFFS | 0 | 0 | 0 |  |  | 0 |  | 0 | 0% | 0 | 0% | 0050301000 | A
Subtotal of T | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | - | - | -

## DATA (hidden)
VarRevenue | VarLabor | VarBurden | VarMatSub | VarDJEOthers | VarProfitPercOnCost | EarnedMHs | ActualMHs | CompositeRateEst | CompositeRateAct

## Sheet7 (hidden)
2025-12-31
| Job | Department | Project Manager | EOPeriodDate | Estimated Manhours | Estimated Gross Margin | Current Labor Performance Factor | Actual Manhour | Actual Gross Margin | Labor performance factorr | Labor Performance Factor cost | bid day Labor Performance Factor | Est%CompleteATYE | JTD Billings | JTD Revenue | overunderbilling | JTD collected | JTD Cost | Net Cash Position | Estimated Composite Rate | Actual Composite rate | Composite Rate Variance | AR Aged Current | ARAged130days | ARAged3160days | ARAged6190days | ARAgedover90days
| 643700 | 0 | J RAMOS | 2025-12-31 | 0 | 0 | 0 | 290 | 14990.1 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 24375.4 | 0 | 0 | 51.69 | 0 | 0 | 0 | 0 | 0 | 0

## Labor Performance (hidden)
ProjectUniqueID | EOPeriodDate | Labor_Performance_Factor | Labor_Performance_Cost | Bid_day_Labor_Performance_Factor