## Query
WITH subqueryTable0 AS (
SELECT
MAX(table0.CorporateFilter__custom) AS CorporateFilter__custom,
MAX(table0.project_manager) AS Project_Manager__custom,
MAX(table0.project_manager) AS projectmanager__standard,
SUM(table0.GM) AS EStimatedGMPct__custom,
'2025-12-31' AS EOPeriodDate,
table0.New_Job_Number AS ProjectUniqueID
FROM
PHASE_MASTER AS table0
WHERE
(
table0.Create_Date_date <= CAST('2025-12-31' as DATE)
)
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable1 AS (
SELECT
SUM(
CASE
WHEN (table1.TXNDATE <= CAST('2025-12-31' as DATE)) THEN table1.Invoice_Amount
END
) AS BilledAmount,
SUM(
CASE
WHEN (table1.TXNDATE <= CAST('2025-12-31' as DATE)) THEN table1.Tran_amount
END
) AS EstimatedTotalCost,
SUM(
CASE
WHEN (table1.TXNDATE <= CAST('2025-12-31' as DATE)) THEN table1.Earned_Revenue
END
) AS JTD_Earned_Revenue_New__custom,
SUM(
CASE
WHEN (table1.TXNDATE <= CAST('2025-12-31' as DATE)) THEN table1.Earned_Revenue
END
) AS EarnedRevenue,
'2025-12-31' AS EOPeriodDate,
table1.Job_Number AS ProjectUniqueID
FROM
EARNED_REVENUE AS table1
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable2 AS (
SELECT
SUM(
CASE
WHEN (table2.END_DATE IN (CAST('2025-12-31' as TIMESTAMP))) THEN table2.REVISED_CONTRACT_AMOUNT
END
) AS CurrentContractAmount,
'2025-12-31' AS EOPeriodDate,
table2.New_Job_Number AS ProjectUniqueID
FROM
CR_CONTRACT AS table2
WHERE
(table2.Company_Code IN ('NAE'))
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable3 AS (
SELECT
SUM(table3.EstGMPerc) AS estimatedgmpercentage__custom,
SUM(table3.PMEstGMPerc) AS pmestimatedgmpercentage__custom,
SUM(table3.EstPercCompAtYE) AS PMEstimateGMPctNew__custom,
'2025-12-31' AS EOPeriodDate,
table3.ProjectUniqueID AS ProjectUniqueID
FROM
PROJECT_REPORTS AS table3
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable4 AS (
SELECT
MAX(table4.Division) AS Division__custom,
MAX(table4.Division) AS Opportunity_Division__custom,
'2025-12-31' AS EOPeriodDate,
table4.New_Job_Number AS ProjectUniqueID
FROM
DIVISION AS table4
WHERE
(table4.Company_Code IN ('NAE'))
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable5 AS (
SELECT
SUM(table5.Payment_Amount) AS Margin,
'2025-12-31' AS EOPeriodDate,
table5.Job_Number AS ProjectUniqueID
FROM
PAY_ADJUSTMENTAS table5
WHERE
(table5.Company_Code IN ('NAE'))
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable6 AS (
SELECT
SUM(table6.Current_Invoice_Balance_Amount) AS CurrentBudget,
SUM(table6.One_Invoice_Balance_Amount) AS ContractCO,
SUM(table6.Thirty_Days_Invoice_Balance_Amount) AS CostsAdj,
SUM(table6.Over_Ninety_Days_Invoice_Balance_Amount) AS PendingContractCO,
SUM(table6.Sixty_Days_Invoice_Balance_Amount) AS PendingCO,
'2025-12-31' AS EOPeriodDate,
table6.Job_Number AS ProjectUniqueID
FROM
AR_AGING AS table6
WHERE
(table6.Company_Code IN ('NAE'))
GROUP BY
EOPeriodDate,
ProjectUniqueID
),
subqueryTable7 AS (
SELECT
SUM(
CASE
WHEN (table7.Cost_Type IN ('B')) THEN table7.Tran_Amount
END
) AS Burden__custom,
'2025-12-31' AS EOPeriodDate,
table7.Job_Number AS ProjectUniqueID
FROM
TRANSACTION AS table7
GROUP BY
EOPeriodDate,
ProjectUniqueID
)
SELECT
MAX(subqueryTable0.CorporateFilter__custom) AS CorporateFilter__custom,
MAX(subqueryTable0.Project_Manager__custom) AS Project_Manager__custom,
MAX(subqueryTable0.projectmanager__standard) AS projectmanager__standard,
SUM(subqueryTable0.EStimatedGMPct__custom) AS EStimatedGMPct__custom,
SUM(subqueryTable1.BilledAmount) AS BilledAmount,
SUM(subqueryTable1.EstimatedTotalCost) AS EstimatedTotalCost,
SUM(subqueryTable1.JTD_Earned_Revenue_New__custom) AS JTD_Earned_Revenue_New__custom,
SUM(subqueryTable1.EarnedRevenue) AS EarnedRevenue,
SUM(subqueryTable2.CurrentContractAmount) AS CurrentContractAmount,
SUM(subqueryTable3.estimatedgmpercentage__custom) AS estimatedgmpercentage__custom,
SUM(subqueryTable3.pmestimatedgmpercentage__custom) AS pmestimatedgmpercentage__custom,
SUM(subqueryTable3.PMEstimateGMPctNew__custom) AS PMEstimateGMPctNew__custom,
MAX(subqueryTable4.Division__custom) AS Division__custom,
MAX(subqueryTable4.Opportunity_Division__custom) AS Opportunity_Division__custom,
SUM(subqueryTable5.Margin) AS Margin,
SUM(subqueryTable6.CurrentBudget) AS CurrentBudget,
SUM(subqueryTable6.ContractCO) AS ContractCO,
SUM(subqueryTable6.CostsAdj) AS CostsAdj,
SUM(subqueryTable6.PendingContractCO) AS PendingContractCO,
SUM(subqueryTable6.PendingCO) AS PendingCO,
SUM(subqueryTable7.Burden__custom) AS Burden__custom,
subqueryTable0.EOPeriodDate AS EOPeriodDate,
subqueryTable0.ProjectUniqueID AS ProjectUniqueID,
CAST('2026-02-01 15:34:59' AS DATETIME) AS BQInsertTimeUTC,
FROM
subqueryTable0
LEFT JOIN subqueryTable1 ON subqueryTable0.EOPeriodDate = subqueryTable1.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable1.ProjectUniqueID
LEFT JOIN subqueryTable2 ON subqueryTable0.EOPeriodDate = subqueryTable2.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable2.ProjectUniqueID
LEFT JOIN subqueryTable3 ON subqueryTable0.EOPeriodDate = subqueryTable3.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable3.ProjectUniqueID
LEFT JOIN subqueryTable4 ON subqueryTable0.EOPeriodDate = subqueryTable4.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable4.ProjectUniqueID
LEFT JOIN subqueryTable5 ON subqueryTable0.EOPeriodDate = subqueryTable5.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable5.ProjectUniqueID
LEFT JOIN subqueryTable6 ON subqueryTable0.EOPeriodDate = subqueryTable6.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable6.ProjectUniqueID
LEFT JOIN subqueryTable7 ON subqueryTable0.EOPeriodDate = subqueryTable7.EOPeriodDate
AND subqueryTable0.ProjectUniqueID = subqueryTable7.ProjectUniqueID
GROUP BY
EOPeriodDate,
ProjectUniqueID

## Project Managers
|  |  | Estimated | [19 empty] | 2025 | [5 empty] | 2026 |  |  |  |  | 2027
Project Manager | Job Number | Description | Current Contract Amount | Estimated Cost | Gross Margin | GM% | JTD Earned Revenue | Cost to Date | Gross Margin to Date | GM % | Billed Amount | Over Billing | (Under) Billing | Backlog | % Complete | PM Estimated GM % | Prior Period Revised PM Estimated GM % | Revised PM Estimated GM % | Potential Profit | Prior Period Revised Potential Profit | Revised Potential Profit | % Complete @ YE | Prior Period Revised % Complete @ YE | Revised % Complete @ YE | Contract Amount | Estimated Cost | Gross Margin | GM % | Revised % Complete @ YE | Contract Amount | Estimated Cost | Gross Margin | GM % | Revised % Complete @ YE | Contract Amount | Estimated Cost | Gross Margin | GM % | Gross Margin | GM % | pmestimatedgmpercentage__custom | Comments
Project Manager | Job Number | Description | Current Contract Amount | Estimated Cost | Gross Margin | GM% | JTD Earned Revenue | Cost to Date | Gross Margin to Date | GM % | Billed Amount | Over Billing | (Under) Billing | Backlog | % Complete | PM Estimated GM % | Prior Period Revised PM Estimated GM % | Revised PM Estimated GM % | Potential Profit | Prior Period Revised Potential Profit | Revised Potential Profit | % Complete @ YE | Prior Period Revised % Complete @ YE | Revised % Complete @ YE | CY Contract Amount | CY Estimated Cost | CY Gross Margin | CY GM % | RevisedCY1 % Complete | CY1 Contract Amount | CY1 Estimated Cost | CY1 Gross Margin | CY1GM% | CY2 Revised % Complete @ YE | CY2 Contract Amount | CY2 Estimated Cost | CY2 Gross Margin | CY2 GM % | estimatedgmpercentage__custom | pmestimatedgmpercentage__custom | percentagecompleteatye__custom | Comments | EStimatedGMPct | Comments
B LIU | 719500 | SWITCH RR NAP 4 | 20845819.02 | 16885113.4062 | 3960705.6138 | 19% | 20845819.02 | 16381246.53 | 4464572.49 | 21.42% | 20845819.02 | 0 | 0 | 0 | 100% | 21% | 21.49% | 21.42% | -110063.9187 | -690.4377 | 766.0271 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0.19 | 0.21
B LIU | 722320 | SPACEX DIRECT WORK | 128026.07 | 106193.439 | 21832.631 | 17.05% | 124814.07 | 103529.19 | 21284.88 | 17.05% | 124814.07 | 0 | 0 | 3212 | 97.49% | 17.05% | 15% | 15% | 0 | -3850.67 | -3015.0229 | 100% | 100% | 100% | 3212 | 2664.249 | 547.751 | 17.05% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 15%
Subtotal of B LIU | - | - | 20973845.09 | 16991306.8452 | 3982538.2448 | - | 20970633.09 | 16484775.72 | 4485857.37 | 21.39% | 20970633.09 | 0 | 0 | 3212 | 99.98% | - | - | - | -110063.9187 | -4541.1077 | -2248.9959 | - | - | - | 3212 | 2664.249 | 547.751 | 17.05% | 0% | 0 | 0 | 0 | 0% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
B ONTIVEROS | 722210 | LIBERTY HILL HS #2 | 11473198 | 9522754.34 | 1950443.66 | 17% | 10565812.7 | 8976901.19 | 1588911.51 | 15.04% | 10673408.75 | 107596.05 | 0 | 907385.3 | 92.09% | 19% | 15% | 15% | 516781.3617 | -4632.4106 | -4752.4765 | 100% | 98.98% | 87% | -584130.44 | -496287.5446 | -87842.8954 | 15.04% | 100% | 1491515.74 | 1267218.1309 | 224297.6091 | 15.04% |  | 0 | 0 | 0 | 0% | 0.17 | 0.19 |  |  | 30%
B ONTIVEROS | 722450 | VALERO AUSTIN PAC OFFICE | 404338.1 | 337510.9479 | 66827.1521 | 16.53% | 395116.39 | 329813.36 | 65303.03 | 16.53% | 404338.1 | 9221.71 | 0 | 9221.71 | 97.72% | 16.53% | 17% | 17% | 0 | 9254.1282 | 2249.104 | 100% | 100% | 100% | 9221.71 | 7697.5879 | 1524.1221 | 16.53% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0%
B ONTIVEROS | 722500 | CORR OSP ADMIN & REC | 9526861 | 7906107.9183 | 1620753.0817 | 17.01% | 233598.07 | 193857.3 | 39740.77 | 17.01% | 268250 | 34651.93 | 0 | 9293262.93 | 2.45% | 17.01% | 15% | 17% | 0 | -2771.5918 | -35.058 | 100% | 11.11% | 5% | 242744.98 | 201448.0959 | 41296.8841 | 17.01% | 100% | 9050517.95 | 7510802.5224 | 1539715.4276 | 17.01% | 100% | 0 | 0 | 0 | 0% |  |  |  |  | 17%
Subtotal of B ONTIVEROS | - | - | 21404397.1 | 17766373.2063 | 3638023.8937 | - | 11194527.16 | 9500571.85 | 1693955.31 | 15.13% | 11345996.85 | 151469.69 | 0 | 10209869.94 | 52.3% | - | - | - | 516781.3617 | 1850.1258 | -2538.4304 | - | - | - | -332163.75 | -287141.8608 | -45021.8892 | 13.55% | 0% | 10542033.69 | 8778020.6533 | 1764013.0367 | 16.73% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
D CASTANEDA | 722400 | WILCO JUVENILE JUSTICE | 10936331.73 | 8858428.7013 | 2077903.0287 | 19% | 2811002.65 | 2342502.19 | 468500.46 | 16.67% | 3561220.13 | 750217.48 | 0 | 8125329.08 | 25.7% | 18% | 17% | 18% | 45707.3378 | 9491.6304 | 45707.3378 | 100% | 33.37% | 26% | 32443.5998 | 27036.333 | 5407.2668 | 16.67% | 100% | 8092885.4802 | 6744071.1807 | 1348814.2995 | 16.67% | 100% | 0 | 0 | 0 | 0% | 0.19 | 0.18 |  |  | 16.7%
D CASTANEDA | 722520 | SPACE X CLEANROOM-HODESS | 8053000 | 6682987.6518 | 1370012.3482 | 17.01% | 886097.52 | 735350.65 | 150746.87 | 17.01% | 1670850 | 784752.48 | 0 | 7166902.48 | 11% | 17.01% | 15% | 20% | 0 | 3675.7847 | 33090.7925 | 100% | 21.59% | 25% | 1127152.48 | 935396.2629 | 191756.2171 | 17.01% | 100% | 6039750 | 5012240.7388 | 1027509.2612 | 17.01% |  | 0 | 0 | 0 | 0% |  |  |  |  | 17%
Subtotal of D CASTANEDA | - | - | 18989331.73 | 15541416.3531 | 3447915.3769 | - | 3697100.17 | 3077852.84 | 619247.33 | 16.75% | 5232070.13 | 1534969.96 | 0 | 15292231.56 | 19.47% | - | - | - | 45707.3378 | 13167.4151 | 78798.1303 | - | - | - | 1159596.0798 | 962432.5959 | 197163.4839 | 17% | 0% | 14132635.4802 | 11756311.9196 | 2376323.5606 | 16.81% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
K HERNANDEZ | 710045 | ZILKER BARTON SPRINGS BAT | 1484896.81 | 1158219.5118 | 326677.2982 | 22% | 1484896.81 | 1465800.35 | 19096.46 | 1.286% | 1484896.81 | 0 | 0 | 0 | 100% | 5% | 1.8% | 1% | 58050.9268 | 6070.7358 | -4290.3959 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0.22 | 0.05 |  |  | 6%
K HERNANDEZ | 718000 | TFC PARK 35 | 4093979.32 | 3398002.8356 | 695976.4844 | 17% | 4093633.32 | 3313579.73 | 780053.59 | 19.06% | 4093633.32 | 0 | 0 | 346 | 99.99% | 19% | 19% | 19% | -2794.1472 | -5913.4805 | -2794.1472 | 100% | 100% | 100% | 346 | 280.0687 | 65.9313 | 19.06% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0.17 | 0.19 |  |  | 22%
K HERNANDEZ | 720900 | TFC GMP4 - BP4- DHNP RENO | 7230488.54 | 6001305.4882 | 1229183.0518 | 17% | 5396691.7 | 4063773.79 | 1332917.91 | 24.7% | 6079333.91 | 682642.21 | 0 | 1833796.84 | 74.64% | 33% | 26% | 25% | 668642.3149 | 346109.8873 | 21673.3533 | 100% | 97.1% | 95% | 1472272.413 | 1108638.8433 | 363633.5697 | 24.7% | 100% | 361524.427 | 272232.2439 | 89292.1831 | 24.7% |  | 0 | 0 | 0 | 0% | 0.17 | 0.33 |  |  | 24.1%
K HERNANDEZ | 722420 | UT MAIN BLDG RESTORATION | 3751721 | 3100595.8858 | 651125.1142 | 17.36% | 1327737.07 | 1097303.37 | 230433.7 | 17.36% | 1172929 | 0 | -154808.07 | 2423983.93 | 35.39% | 17.36% | 17% | 17% | 0 | -5191.8275 | -5684.817 | 100% | 52.62% | 40% | 172951.33 | 142934.9843 | 30016.3457 | 17.36% | 100% | 2251032.6 | 1860357.5315 | 390675.0685 | 17.36% |  | 0 | 0 | 0 | 0% |  |  |  |  | 17.4%
Subtotal of K HERNANDEZ | - | - | 16561085.67 | 13658123.7214 | 2902961.9486 | - | 12302958.9 | 9940457.24 | 2362501.66 | 19.2% | 12830793.04 | 682642.21 | -154808.07 | 4258126.77 | 74.29% | - | - | - | 723899.0946 | 341075.3152 | 8903.9933 | - | - | - | 1645569.743 | 1251853.8963 | 393715.8467 | 23.93% | 0% | 2612557.027 | 2132589.7753 | 479967.2517 | 18.37% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
M CASELLA | 722280 | HUTTO 1 INITIAL IMPROV | 13617357 | 11438579.88 | 2178777.12 | 16% | 13617357 | 12370709.69 | 1246647.31 | 9.155% | 13617357 | 0 | 0 | 0 | 100% | 23% | 9% | 8.5% | 2448499.7403 | -143371.433 | -97455.6995 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0.16 | 0.23 |  |  | 10%
M CASELLA | 722340 | DEL VALLE LIBRARY | 1188326 | 986310.58 | 202015.42 | 17% | 364066.55 | 316579.52 | 47487.03 | 13.04% | 259600 | 0 | -104466.55 | 824259.45 | 30.64% | 18% | 12% | 13% | 22006.0354 | -3314.9436 | -182.0443 | 100% | 46.47% | 30% | -7568.75 | -6581.5199 | -987.2301 | 13.04% | 100% | 831828.2 | 723328.6669 | 108499.5331 | 13.04% |  | 0 | 0 | 0 | 0% | 0.17 | 0.18 |  |  | 13%
M CASELLA | 722470 | TSTC HUTTO | 585596.97 | 485972.5748 | 99624.3952 | 17.01% | 177100 | 146970.95 | 30129.05 | 17.01% | 398194.97 | 221094.97 | 0 | 408496.97 | 30.24% | 17.01% | 17% | 17% | 0 | -25.9943 | -26.5663 | 100% | 64.8% | 90% | 349937.273 | 290404.3673 | 59532.9057 | 17.01% | 100% | 58559.697 | 48597.2575 | 9962.4395 | 17.01% |  | 0 | 0 | 0 | 0% |  |  |  |  | 17%
Subtotal of M CASELLA | - | - | 15391279.97 | 12910863.0348 | 2480416.9352 | - | 14158523.55 | 12834260.16 | 1324263.39 | 9.353% | 14275151.97 | 221094.97 | -104466.55 | 1232756.42 | 91.99% | - | - | - | 2470505.7756 | -146712.3709 | -97664.31 | - | - | - | 342368.523 | 283822.8474 | 58545.6756 | 17.1% | 0% | 890387.897 | 771925.9244 | 118461.9726 | 13.3% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
T FERGUSON | 718100 | TESLA 2022 PLASTIC FEEDER | 898831.39 | 728053.4259 | 170777.9641 | 19% | 898831.39 | 744578.07 | 154253.32 | 17.16% | 898831.39 | 0 | 0 | 0 | 100% | 17% | 8% | 7% | -1749.378 | -89507.4009 | -98209.8094 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0.19 | 0.17
T FERGUSON | 719900 | BLOCKER LANE D14 | 10000 | 10000 | 0 | 0% | 6910.28 | 6910.28 | 0 | 0% |  | 0 | -6910.28 | 3089.72 | 69.1% | 0% | 17% | 17% | 0 | 1415.3586 | 1415.3586 | 100% | 100% | 100% | 3089.72 | 3089.72 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0 | 0
T FERGUSON | 720500 | UTFC4 | 972890 | 865872.1 | 107017.9 | 11% | 972890 | 847449.19 | 125440.81 | 12.89% | 972890 | 0 | 0 | 0 | 100% | 12% | 13% | 13% | -9879.5568 | -487.0154 | 1189.5287 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0.11 | 0.12 |  |  | 13%
T FERGUSON | 722200 | TITO'S BLOCKER LN W7 | 10801639 | 8857343.98 | 1944295.02 | 18% | 10200547.38 | 6443807.57 | 3756739.81 | 36.83% | 10801639 | 601091.62 | 0 | 601091.62 | 94.44% | 36% | 36% | 39% | -132098.0519 | 150995.0156 | 363071.5872 | 100% | 99.83% | 98% | 385058.84 | 243246.2667 | 141812.5733 | 36.83% | 100% | 216032.78 | 136470.4865 | 79562.2935 | 36.83% |  | 0 | 0 | 0 | 0% | 0.18 | 0.36
T FERGUSON | 722201 | TITOS D16 | 540613 | 432490.3516 | 108122.6484 | 20% | 536266.36 | 429013.04 | 107253.32 | 20% | 540613 | 4346.64 | 0 | 4346.64 | 99.2% | 20% | 17% | 20% | 0 | 2008.2646 | -0.06 | 100% | 98.12% | 95% | -22684.01 | -18147.206 | -4536.804 | 20% | 100% | 27030.65 | 21624.5176 | 5406.1324 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722202 | TITOS D17 | 540613 | 432490.261 | 108122.739 | 20% | 264539.26 | 211631.34 | 52907.92 | 20% | 540613 | 276073.74 | 0 | 276073.74 | 48.93% | 20% | 17% | 20% | 0 | 979.5722 | -0.085 | 100% | 86.28% | 95% | 249043.09 | 199234.408 | 49808.682 | 20% | 100% | 27030.65 | 21624.5131 | 5406.1369 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722203 | TITOS D18 | 540613 | 432490.3775 | 108122.6225 | 20% | 529491.34 | 423593.05 | 105898.29 | 20% | 540613 | 11121.66 | 0 | 11121.66 | 97.94% | 20% | 17% | 20% | 0 | 2003.3175 | -0.0275 | 100% | 98.07% | 95% | -15908.99 | -12727.1913 | -3181.7987 | 20% | 100% | 27030.65 | 21624.5189 | 5406.1311 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722204 | TITOS D19 | 540613 | 432490.364 | 108122.636 | 20% | 511281.68 | 409025.31 | 102256.37 | 20% | 540613 | 29331.32 | 0 | 29331.32 | 94.57% | 20% | 17% | 20% | -5.8208e-11 | 1919.9359 | -0.0425 | 100% | 97.11% | 95% | 2300.67 | 1840.5358 | 460.1342 | 20% | 100% | 27030.65 | 21624.5182 | 5406.1318 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722205 | NEW COMPRESSOR BLDG | 97115 | 63102.6763 | 34012.3237 | 35.02% | 71722.08 | 46603.05 | 25119.03 | 35.02% | 97115 | 25392.92 | 0 | 25392.92 | 73.85% | 35.02% | 15% | 35% | 0 | -3426.7324 | -25.08 | 100% | 100% | 100% | 25392.92 | 16499.6263 | 8893.2937 | 35.02% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 35%
T FERGUSON | 722206 | TITOS GUARD HOUSE 6 | 101940 | 99235.31 | 2704.69 | 2.653% | 101940 | 99235.31 | 2704.69 | 2.653% | 101940 | 0 | 0 | 0 | 100% | 2.653% | 15% | 2.65% | 0 | -2333.9465 | -3.3693 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 16.7%
T FERGUSON | 722207 | TITOS DUNNAGE AREA DA-1 | 223936.85 | 186614.0637 | 37322.7863 | 16.67% | 186692.87 | 155577.41 | 31115.46 | 16.67% | 223936.85 | 37243.98 | 0 | 37243.98 | 83.37% | 16.67% | 20% | 20% | 0 | 7778.8925 | 7778.8925 | 100% | 100% | 100% | 37243.98 | 31036.6537 | 6207.3263 | 16.67% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 16.7%
T FERGUSON | 722208 | TITOS AT VAULT EXPANSION | 155587 | 124469.483 | 31117.517 | 20% | 29248.64 | 23398.89 | 5849.75 | 20% | 29762 | 513.36 | 0 | 126338.36 | 18.8% | 20% | 20% | 20% | -3.638e-12 | -0.0225 | -0.0275 | 100% | 31.7% | 20% | 1868.76 | 1495.0066 | 373.7534 | 20% | 100% | 124469.6 | 99575.5864 | 24894.0136 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722330 | WILCO HQ | 8047533.49 | 6679452.7967 | 1368080.6933 | 17% | 6563124.95 | 5446576.63 | 1116548.32 | 17.01% | 6409924.44 | 0 | -153200.51 | 1484408.54 | 81.55% | 22% | 21% | 20% | 419665.6013 | 71486.0184 | 245095.8375 | 100% | 89.56% | 90% | 679655.191 | 564029.1946 | 115625.9964 | 17.01% | 100% | 804753.349 | 667845.0916 | 136908.2574 | 17.01% |  | 0 | 0 | 0 | 0% | 0.17 | 0.22 |  |  | 17%
T FERGUSON | 722460 | TITOS BACK OF LINE IMPROV | 161110 | 128887.931 | 32222.069 | 20% | 102807.23 | 82245.74 | 20561.49 | 20% | 155528 | 52720.77 | 0 | 58302.77 | 63.81% | 20% | 20% | 22% | 0 | -0.055 | 2636.0264 | 100% | 96.31% | 80% | 26080.77 | 20864.6048 | 5216.1652 | 20% | 100% | 32222 | 25777.5862 | 6444.4138 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722480 | TITOS D 14 PWR / SECURITY | 70972.07 | 71113.38 | -141.31 | -0.1991% | 70972.07 | 71113.38 | -141.31 | -0.1991% | 70972.07 | 0 | 0 | 0 | 100% | -0.1991% | 25% | 0% | 0 | 19975.1033 | 141.31 | 100% | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0%
T FERGUSON | 722510 | D2&D3 FA CONDUITS | 22500 | 17999.9569 | 4500.0431 | 20% | 9406.26 | 7524.99 | 1881.27 | 20% | 22500 | 13093.74 | 0 | 13093.74 | 41.81% | 20% | 20% | 30% | 0 | -0.01 | 1343.7257 | 100% | 63.42% | 50% | 1843.74 | 1474.9885 | 368.7515 | 20% | 100% | 11250 | 8999.9785 | 2250.0215 | 20% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722530 | W7 B-VAULTS | 70673.08 | 56538.4534 | 14134.6266 | 20% | 66973.35 | 53578.67 | 13394.68 | 20% | 37427.44 | 0 | -29545.91 | 3699.73 | 94.77% | 20% | 20% | 20% | 0 | -0.0075 | -0.0125 | 100% | 49.77% | 100% | 3699.73 | 2959.7834 | 739.9466 | 20% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722540 | TITOS GOLF CART CHARGERS | 846 | 761.4 | 84.6 | 10% |  |  | 0 | 0% | 846 | 846 | 0 | 846 | 0% | 10% | 10% | 25% | 0 | 0 | 0 | 100% | 15% | 100% | 846 | 846 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 10%
T FERGUSON | 722550 | W2 MDF ROOM | 2574 | 2059.1945 | 514.8055 | 20% | 1883.73 | 1506.98 | 376.75 | 20% | 2574 | 690.27 | 0 | 690.27 | 73.18% | 20% | 20% | 20% | 0 | 0 | -0.005 | 100% | 35.48% | 100% | 690.27 | 552.2145 | 138.0555 | 20% | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
T FERGUSON | 722560 | PROJECT COSMOS | 1212523 | 1212523 | 0 | 0% |  |  | 0 | 0% |  | 0 | 0 | 1212523 | 0% | 0% |  | 20% | 0 |  | 0 | 100% |  | 2% | 24250.46 | 24250.46 | 0 | 0% | 100% | 1188272.54 | 1188272.54 | 0 | 0% |  | 0 | 0 | 0 | 0%
Subtotal of T FERGUSON | - | - | 25013122.88 | 20833988.5058 | 4179134.3742 | - | 21125528.87 | 15503368.9 | 5622159.97 | 26.61% | 21988338.19 | 1052466.02 | -189656.7 | 3887594.01 | 84.46% | - | - | - | 275938.6146 | 162806.2884 | 524433.748 | - | - | - | 1402471.141 | 1080545.0657 | 321926.0753 | 22.95% | 0% | 2485122.869 | 2213439.3369 | 271683.5321 | 10.93% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
YE ACCRUAL | 999996 | CTX CONST ACCRUAL JOB | 0 | 0 | 0 | 20% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 20% | 0% |  | 0 | 0 | 0 | 100% | 0% |  | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% |  |  |  |  | 20%
Subtotal of YE ACCRUAL | - | - | 0 | 0 | 0 | - | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | - | - | - | 0 | 0 | 0 | - | - | - | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
Grand Total | - | - | 118333062.44 | 97702071.6665 | 20630990.7735 | - | 83449271.74 | 67341286.71 | 16107985.03 | 19.3% | 86642983.27 | 3642642.85 | -448931.32 | 34883790.7 | 70.52% | - | - | - | 3922768.2657 | 367645.6659 | 509684.1353 | - | - | - | 4221053.7368 | 3294176.7935 | 926876.9433 | 21.96% | 0% | 30662736.9632 | 25652287.6095 | 5010449.3537 | 16.34% | - | 0 | 0 | 0 | 0% | - | - | - | - | -
Note on T12: Override Value: 21.42%
Note on Z12: Override Value: 100.00%
Note on T13: Override Value: 15.00%
Note on Z13: Override Value: 100.00%
Note on T15: Override Value: 15.00%
Note on Z15: Override Value: 87.00%
Note on T16: Override Value: 17.00%
Note on Z16: Override Value: 100.00%
Note on T17: Override Value: 17.00%
Note on Z17: Override Value: 5.00%
Note on AJ17: Override Value: 100.00%
Note on T19: Override Value: 18.00%
Note on Z19: Override Value: 26.00%
Note on AJ19: Override Value: 100.00%
Note on T20: Override Value: 20.00%
Note on Z20: Override Value: 25.00%
Note on T22: Override Value: 1.00%
Note on Z22: Override Value: 100.00%
Note on T23: Override Value: 19.00%
Note on Z23: Override Value: 100.00%
Note on T24: Override Value: 25.00%
Note on Z24: Override Value: 95.00%
Note on T25: Override Value: 17.00%
Note on Z25: Override Value: 40.00%
Note on T27: Override Value: 8.50%
Note on Z27: Override Value: 100.00%
Note on T28: Override Value: 13.00%
Note on Z28: Override Value: 30.00%
Note on T29: Override Value: 17.00%
Note on Z29: Override Value: 90.00%
Note on T31: Override Value: 7.00%
Note on Z31: Override Value: 100.00%
Note on T32: Override Value: 17.00%
Note on Z32: Override Value: 100.00%
Note on T33: Override Value: 13.00%
Note on Z33: Override Value: 100.00%
Note on T34: Override Value: 39.00%
Note on Z34: Override Value: 98.00%
Note on T35: Override Value: 20.00%
Note on Z35: Override Value: 95.00%
Note on T36: Override Value: 20.00%
Note on Z36: Override Value: 95.00%
Note on T37: Override Value: 20.00%
Note on Z37: Override Value: 95.00%
Note on T38: Override Value: 20.00%
Note on Z38: Override Value: 95.00%
Note on T39: Override Value: 35.00%
Note on Z39: Override Value: 100.00%
Note on T40: Override Value: 2.65%
Note on Z40: Override Value: 100.00%
Note on T41: Override Value: 20.00%
Note on Z41: Override Value: 100.00%
Note on T42: Override Value: 20.00%
Note on Z42: Override Value: 20.00%
Note on T43: Override Value: 20.00%
Note on Z43: Override Value: 90.00%
Note on T44: Override Value: 22.00%
Note on Z44: Override Value: 80.00%
Note on T45: Override Value: 0.00%
Note on Z45: Override Value: 100.00%
Note on T46: Override Value: 30.00%
Note on Z46: Override Value: 50.00%
Note on T47: Override Value: 20.00%
Note on Z47: Override Value: 100.00%
Note on T48: Override Value: 25.00%
Note on Z48: Override Value: 100.00%
Note on T49: Override Value: 20.00%
Note on Z49: Override Value: 100.00%
Note on T50: Override Value: 20.00%
Note on Z50: Override Value: 2.00%

## Divisions
Over and Under Billings
2025-11-30
|  |  | Estimated | [18 empty] | 2025 |  |  |  | 2026 |  |  |  |  | 2027
Division | Job Number | Description | Current Contract Amount | Estimated Cost | Gross Margin | GM% | JTD Earned Revenue | Cost to Date | Gross Margin to Date | GM % | Billed Amount | Over Billing | (Under) Billing | Backlog | % Complete | PM Estimated GM % | Revised PM Estimated GM % | Potential Profit | Revised Potential Profit | % Complete @ YE | Revised % Complete @ YE | Contract Amount | Estimated Cost | Gross Margin | GM % | Revised % Complete @ YE | Contract Amount | Estimated Cost | Gross Margin | GM % | Revised % Complete @ YE | Contract Amount | Estimated Cost | Gross Margin | GM % | GM % | pmestimatedgmpercentage__custom | percentagecompleteatye__custom | Comments
Division | Job Number | Description | Current Contract Amount | Estimated Cost | Gross Margin | GM% | JTD Earned Revenue | Cost to Date | Gross Margin to Date | GM % | Billed Amount | Over Billing | (Under) Billing | Backlog | % Complete | PM Estimated GM % | Revised PM Estimated GM % | Potential Profit | Revised Potential Profit | % Complete @ YE | Revised % Complete @ YE | CY Contract Amount | CY Estimated Cost | CY Gross Margin | CY GM % | CY Revised % Complete | CY1 Contract Amount | CY1 Estimated Cost | CY1 Gross Margin | CY1GM% | CY2 Revised % Complete @ YE | CY2 Contract Amount | CY2 Estimated Cost | CY2 Gross Margin | CY2 GM % | estimatedgmpercentage__custom | pmestimatedgmpercentage__custom | percentagecompleteatye__custom | Comments
Central Texas Electrical Construction | 710045 | ZILKER BARTON SPRINGS BAT | 1484896.81 | 1158219.5118 | 326677.2982 | 22% | 1484896.81 | 1465800.35 | 19096.46 | 1.286% | 1484896.81 | 0 | 0 | 0 | 100% | 5% | 1% | 58050.9268 | -4290.3959 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0.22 | 0.05 |  | 0
Central Texas Electrical Construction | 718000 | TFC PARK 35 | 4093979.32 | 3398002.8356 | 695976.4844 | 17% | 4093633.32 | 3313579.73 | 780053.59 | 19.06% | 4093633.32 | 0 | 0 | 346 | 99.99% | 19% | 19% | -2794.1472 | -2794.1472 | 100% | 100% | 346 | 280.0687 | 65.9313 | 19.06% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0.17 | 0.19 |  | 0
Central Texas Electrical Construction | 718100 | TESLA 2022 PLASTIC FEEDER | 898831.39 | 728053.4259 | 170777.9641 | 19% | 898831.39 | 744578.07 | 154253.32 | 17.16% | 898831.39 | 0 | 0 | 0 | 100% | 17% | 7% | -1749.378 | -98209.8094 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0.19 | 0.17 |  | 0
Central Texas Electrical Construction | 719500 | SWITCH RR NAP 4 | 20845819.02 | 16885113.4062 | 3960705.6138 | 19% | 20845819.02 | 16381246.53 | 4464572.49 | 21.42% | 20845819.02 | 0 | 0 | 0 | 100% | 21% | 21.42% | -110063.9187 | 766.0271 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0.19 | 0.21 |  | 0
Central Texas Electrical Construction | 719900 | BLOCKER LANE D14 | 10000 | 10000 | 0 | 0% | 6910.28 | 6910.28 | 0 | 0% |  | 0 | -6910.28 | 3089.72 | 69.1% | 0% | 17% | 0 | 1415.3586 | 100% | 100% | 3089.72 | 3089.72 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0 | 0 |  | 0
Central Texas Electrical Construction | 720500 | UTFC4 | 972890 | 865872.1 | 107017.9 | 11% | 972890 | 847449.19 | 125440.81 | 12.89% | 972890 | 0 | 0 | 0 | 100% | 12% | 13% | -9879.5568 | 1189.5287 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0.11 | 0.12 |  | 0
Central Texas Electrical Construction | 720900 | TFC GMP4 - BP4- DHNP RENO | 7230488.54 | 6001305.4882 | 1229183.0518 | 17% | 5396691.7 | 4063773.79 | 1332917.91 | 24.7% | 6079333.91 | 682642.21 | 0 | 1833796.84 | 74.64% | 33% | 25% | 668642.3149 | 21673.3533 | 100% | 95% | 1472272.413 | 1108638.8433 | 363633.5697 | 24.7% | 100% | 361524.427 | 272232.2439 | 89292.1831 | 24.7% | 0% | 0 | 0 | 0 | 0% | 0.17 | 0.33 |  | 0
Central Texas Electrical Construction | 722200 | TITO'S BLOCKER LN W7 | 10801639 | 8857343.98 | 1944295.02 | 18% | 10200547.38 | 6443807.57 | 3756739.81 | 36.83% | 10801639 | 601091.62 | 0 | 601091.62 | 94.44% | 36% | 39% | -132098.0519 | 363071.5872 | 100% | 98% | 385058.84 | 243246.2667 | 141812.5733 | 36.83% | 100% | 216032.78 | 136470.4865 | 79562.2935 | 36.83% | 0% | 0 | 0 | 0 | 0% | 0.18 | 0.36 |  | 0
Central Texas Electrical Construction | 722201 | TITOS D16 | 540613 | 432490.3516 | 108122.6484 | 20% | 536266.36 | 429013.04 | 107253.32 | 20% | 540613 | 4346.64 | 0 | 4346.64 | 99.2% | 20% | 20% | 0 | -0.06 | 100% | 95% | -22684.01 | -18147.206 | -4536.804 | 20% | 100% | 27030.65 | 21624.5176 | 5406.1324 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722202 | TITOS D17 | 540613 | 432490.261 | 108122.739 | 20% | 264539.26 | 211631.34 | 52907.92 | 20% | 540613 | 276073.74 | 0 | 276073.74 | 48.93% | 20% | 20% | 0 | -0.085 | 100% | 95% | 249043.09 | 199234.408 | 49808.682 | 20% | 100% | 27030.65 | 21624.5131 | 5406.1369 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722203 | TITOS D18 | 540613 | 432490.3775 | 108122.6225 | 20% | 529491.34 | 423593.05 | 105898.29 | 20% | 540613 | 11121.66 | 0 | 11121.66 | 97.94% | 20% | 20% | 0 | -0.0275 | 100% | 95% | -15908.99 | -12727.1913 | -3181.7987 | 20% | 100% | 27030.65 | 21624.5189 | 5406.1311 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722204 | TITOS D19 | 540613 | 432490.364 | 108122.636 | 20% | 511281.68 | 409025.31 | 102256.37 | 20% | 540613 | 29331.32 | 0 | 29331.32 | 94.57% | 20% | 20% | -5.8208e-11 | -0.0425 | 100% | 95% | 2300.67 | 1840.5358 | 460.1342 | 20% | 100% | 27030.65 | 21624.5182 | 5406.1318 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722205 | NEW COMPRESSOR BLDG | 97115 | 63102.6763 | 34012.3237 | 35.02% | 71722.08 | 46603.05 | 25119.03 | 35.02% | 97115 | 25392.92 | 0 | 25392.92 | 73.85% | 35.02% | 35% | 0 | -25.08 | 100% | 100% | 25392.92 | 16499.6263 | 8893.2937 | 35.02% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722206 | TITOS GUARD HOUSE 6 | 101940 | 99235.31 | 2704.69 | 2.653% | 101940 | 99235.31 | 2704.69 | 2.653% | 101940 | 0 | 0 | 0 | 100% | 2.653% | 2.65% | 0 | -3.3693 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722207 | TITOS DUNNAGE AREA DA-1 | 223936.85 | 186614.0637 | 37322.7863 | 16.67% | 186692.87 | 155577.41 | 31115.46 | 16.67% | 223936.85 | 37243.98 | 0 | 37243.98 | 83.37% | 16.67% | 20% | 0 | 7778.8925 | 100% | 100% | 37243.98 | 31036.6537 | 6207.3263 | 16.67% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722208 | TITOS AT VAULT EXPANSION | 155587 | 124469.483 | 31117.517 | 20% | 29248.64 | 23398.89 | 5849.75 | 20% | 29762 | 513.36 | 0 | 126338.36 | 18.8% | 20% | 20% | -3.638e-12 | -0.0275 | 100% | 20% | 1868.76 | 1495.0066 | 373.7534 | 20% | 100% | 124469.6 | 99575.5864 | 24894.0136 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722210 | LIBERTY HILL HS #2 | 11473198 | 9522754.34 | 1950443.66 | 17% | 10565812.7 | 8976901.19 | 1588911.51 | 15.04% | 10673408.75 | 107596.05 | 0 | 907385.3 | 92.09% | 19% | 15% | 516781.3617 | -4752.4765 | 100% | 87% | -584130.44 | -496287.5446 | -87842.8954 | 15.04% | 100% | 1491515.74 | 1267218.1309 | 224297.6091 | 15.04% | 0% | 0 | 0 | 0 | 0% | 0.17 | 0.19 |  | 0
Central Texas Electrical Construction | 722280 | HUTTO 1 INITIAL IMPROV | 13617357 | 11438579.88 | 2178777.12 | 16% | 13617357 | 12370709.69 | 1246647.31 | 9.155% | 13617357 | 0 | 0 | 0 | 100% | 23% | 8.5% | 2448499.7403 | -97455.6995 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0.16 | 0.23 |  | 0
Central Texas Electrical Construction | 722320 | SPACEX DIRECT WORK | 128026.07 | 106193.439 | 21832.631 | 17.05% | 124814.07 | 103529.19 | 21284.88 | 17.05% | 124814.07 | 0 | 0 | 3212 | 97.49% | 17.05% | 15% | 0 | -3015.0229 | 100% | 100% | 3212 | 2664.249 | 547.751 | 17.05% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722330 | WILCO HQ | 8047533.49 | 6679452.7967 | 1368080.6933 | 17% | 6563124.95 | 5446576.63 | 1116548.32 | 17.01% | 6409924.44 | 0 | -153200.51 | 1484408.54 | 81.55% | 22% | 20% | 419665.6013 | 245095.8375 | 100% | 90% | 679655.191 | 564029.1946 | 115625.9964 | 17.01% | 100% | 804753.349 | 667845.0916 | 136908.2574 | 17.01% | 0% | 0 | 0 | 0 | 0% | 0.17 | 0.22 |  | 0
Central Texas Electrical Construction | 722340 | DEL VALLE LIBRARY | 1188326 | 986310.58 | 202015.42 | 17% | 364066.55 | 316579.52 | 47487.03 | 13.04% | 259600 | 0 | -104466.55 | 824259.45 | 30.64% | 18% | 13% | 22006.0354 | -182.0443 | 100% | 30% | -7568.75 | -6581.5199 | -987.2301 | 13.04% | 100% | 831828.2 | 723328.6669 | 108499.5331 | 13.04% | 0% | 0 | 0 | 0 | 0% | 0.17 | 0.18 |  | 0
Central Texas Electrical Construction | 722400 | WILCO JUVENILE JUSTICE | 10936331.73 | 8858428.7013 | 2077903.0287 | 19% | 2811002.65 | 2342502.19 | 468500.46 | 16.67% | 3561220.13 | 750217.48 | 0 | 8125329.08 | 25.7% | 18% | 18% | 45707.3378 | 45707.3378 | 100% | 26% | 32443.5998 | 27036.333 | 5407.2668 | 16.67% | 100% | 8092885.4802 | 6744071.1807 | 1348814.2995 | 16.67% | 100% | 0 | 0 | 0 | 0% | 0.19 | 0.18 |  | 0
Central Texas Electrical Construction | 722420 | UT MAIN BLDG RESTORATION | 3751721 | 3100595.8858 | 651125.1142 | 17.36% | 1327737.07 | 1097303.37 | 230433.7 | 17.36% | 1172929 | 0 | -154808.07 | 2423983.93 | 35.39% | 17.36% | 17% | 0 | -5684.817 | 100% | 40% | 172951.33 | 142934.9843 | 30016.3457 | 17.36% | 100% | 2251032.6 | 1860357.5315 | 390675.0685 | 17.36% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722450 | VALERO AUSTIN PAC OFFICE | 404338.1 | 337510.9479 | 66827.1521 | 16.53% | 395116.39 | 329813.36 | 65303.03 | 16.53% | 404338.1 | 9221.71 | 0 | 9221.71 | 97.72% | 16.53% | 17% | 0 | 2249.104 | 100% | 100% | 9221.71 | 7697.5879 | 1524.1221 | 16.53% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722460 | TITOS BACK OF LINE IMPROV | 161110 | 128887.931 | 32222.069 | 20% | 102807.23 | 82245.74 | 20561.49 | 20% | 155528 | 52720.77 | 0 | 58302.77 | 63.81% | 20% | 22% | 0 | 2636.0264 | 100% | 80% | 26080.77 | 20864.6048 | 5216.1652 | 20% | 100% | 32222 | 25777.5862 | 6444.4138 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722470 | TSTC HUTTO | 585596.97 | 485972.5748 | 99624.3952 | 17.01% | 177100 | 146970.95 | 30129.05 | 17.01% | 398194.97 | 221094.97 | 0 | 408496.97 | 30.24% | 17.01% | 17% | 0 | -26.5663 | 100% | 90% | 349937.273 | 290404.3673 | 59532.9057 | 17.01% | 100% | 58559.697 | 48597.2575 | 9962.4395 | 17.01% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722480 | TITOS D 14 PWR / SECURITY | 70972.07 | 71113.38 | -141.31 | -0.1991% | 70972.07 | 71113.38 | -141.31 | -0.1991% | 70972.07 | 0 | 0 | 0 | 100% | -0.1991% | 0% | 0 | 141.31 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722500 | CORR OSP ADMIN & REC | 9526861 | 7906107.9183 | 1620753.0817 | 17.01% | 233598.07 | 193857.3 | 39740.77 | 17.01% | 268250 | 34651.93 | 0 | 9293262.93 | 2.452% | 17.01% | 17% | 0 | -35.058 | 100% | 5% | 242744.98 | 201448.0959 | 41296.8841 | 17.01% | 100% | 9050517.95 | 7510802.5224 | 1539715.4276 | 17.01% | 100% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722510 | D2&D3 FA CONDUITS | 22500 | 17999.9569 | 4500.0431 | 20% | 9406.26 | 7524.99 | 1881.27 | 20% | 22500 | 13093.74 | 0 | 13093.74 | 41.81% | 20% | 30% | 0 | 1343.7257 | 100% | 50% | 1843.74 | 1474.9885 | 368.7515 | 20% | 100% | 11250 | 8999.9785 | 2250.0215 | 20% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722520 | SPACE X CLEANROOM-HODESS | 8053000 | 6682987.6518 | 1370012.3482 | 17.01% | 886097.52 | 735350.65 | 150746.87 | 17.01% | 1670850 | 784752.48 | 0 | 7166902.48 | 11% | 17.01% | 20% | 0 | 33090.7925 | 100% | 25% | 1127152.48 | 935396.2629 | 191756.2171 | 17.01% | 100% | 6039750 | 5012240.7388 | 1027509.2612 | 17.01% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722530 | W7 B-VAULTS | 70673.08 | 56538.4534 | 14134.6266 | 20% | 66973.35 | 53578.67 | 13394.68 | 20% | 37427.44 | 0 | -29545.91 | 3699.73 | 94.77% | 20% | 20% | 0 | -0.0125 | 100% | 100% | 3699.73 | 2959.7834 | 739.9466 | 20% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722540 | TITOS GOLF CART CHARGERS | 846 | 761.4 | 84.6 | 10% |  |  | 0 | 0% | 846 | 846 | 0 | 846 | 0% | 10% | 25% | 0 | 0 | 100% | 100% | 846 | 846 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722550 | W2 MDF ROOM | 2574 | 2059.1945 | 514.8055 | 20% | 1883.73 | 1506.98 | 376.75 | 20% | 2574 | 690.27 | 0 | 690.27 | 73.18% | 20% | 20% | 0 | -0.005 | 100% | 100% | 690.27 | 552.2145 | 138.0555 | 20% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 722560 | PROJECT COSMOS | 1212523 | 1212523 | 0 | 0% |  |  | 0 | 0% |  | 0 | 0 | 1212523 | 0% | 0% | 20% | 0 | 0 | 100% | 2% | 24250.46 | 24250.46 | 0 | 0% | 100% | 1188272.54 | 1188272.54 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Central Texas Electrical Construction | 999996 | CTX CONST ACCRUAL JOB | 0 | 0 | 0 | 20% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 20% | 0% | 0 | 0 | 100% | 0% | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% |  |  |  | 0
Grand Total | - | - | 118333062.44 | 97702071.6665 | 20630990.7735 | - | 83449271.74 | 67341286.71 | 16107985.03 | 19.3% | 86642983.27 | 3642642.85 | -448931.32 | 34883790.7 | 70.52% | - | - | 3922768.2657 | 509684.1353 | - | - | 4221053.7368 | 3294176.7935 | 926876.9433 | - | - | 30662736.9632 | 25652287.6095 | 5010449.3537 | - | - | 0 | 0 | 0 | - | - | - | - | -

## EOperiodDate (hidden)
End of Period Date
2025-11-30